## Sheet1
For Verification and validation see Verification and Validation plan document
Requirement ID | List of Requirements | Source | Notes | Succsess | Failure | Additional Notes
1 | Minimum Working Envolope | Project Brief | Defined as 50cm | Shorterned the car and hollowed out more of it to decrease weight, still reach the 50cm working envelope | - Had a new bar made which was too long and heavy
2 | Design a gripper | Project Brief | Has to pickup a resistor | Can pick up the resitor
3 | Project budget limit of £75 | Project Brief | Budget limmitation | We didnt go over the budget
4 | Measures and moves resistor within 10 seconds | Stakeholder - University |  | Can do it in sub 10 seconds
5 | Be able to sort 12 resitors, and collect all unknow resistors in one location | Stakeholders | All E12 resistors should be sorted with any additional beeing seperated | Acheved
6 | 5 Year lifetime | Stakeholder - Labs | We cant test this but through the verification and validation plan the reliability can be shown | Acheved |  | All parts are rates for greater than 5 years of use under certain conditions
7 | Factor of safety : 1 | Stakeholder - Labs | Not a strugtual part so has a low FoS | Acheved
8 | Be ablt to lift 267mg | Stakeholders | This is the average weight of an E12 resistor | We were able to lift the resistor
9 | Sort resistors into the correct box 99% of the time | Stakeholders | This is essentally 100% but validating 100% correct sorting is impossible | Through testing the robot was correct all the time
10 | Health and saftey documentation | Stakeholders | To go with every order | Curated and included in files
11 | Affordable | Stakeholders | Not much more expensive than the base arm | Under budget
12 | Bluetooth | Stakeholders | Dont need to be connected to the arm by a wire |  |  | Ordered
13 | App controlled | Stakeholders | possibility to use your phone to controll the arm |  | Unfortunatly out of scope for the MVP
14 | Robot price competative | Stakeholder