## Sheet1
Name | Role | Project Initiation |  |  | Project Planning |  |  |  |  | Project Development | [11 empty] | Project Close
|  | Define Scope | Define Roles | Define stakeholders | Define Design Requiremenmts | Financial Plan | Health and Saftey Plan | Interlectual Property Protection | Select bought components | Design Electrical Components | Program Arm | Test Electrical Components | Calculate Arm Geometry | Modify Arm | Test Arm | Design Gripper | Model Gripper in CAD | Manufacture and fit Gripper | Assemble Mimimum Viable Product (MVP) | Test MVP in set conditions | Test MVP in not set conditions | Set up production line | Build first batch
Dominic | Project Manager | R | R | R | A | A | C | C | A | C | I | I | C | C | A | C | R | C | A | R | R | A | A | Dominic | Key
James | Electronics and Programming Lead | R |  | C | R | C |  | I | R | R | R | R |  |  | R |  | C | C | R | R | R | C | C | James | R = RESPONSIBILITY
John | 3D Design and Mechanical Manager | R |  | C | R | C | I | I | R | I | C |  | A | R | R | R | C | R | R | R | R | C | C | John | A = ACCOUNTABILITY
Saad | Algorithmic and mathematical Lead | R |  | C | R | C |  | I | C | I | C |  | R | A | R | C | I | I | I | R | R | C | C | Saad | C = CONSULTATION
Emre | Technical Advisor | R |  | C | R | R | R | R | I |  |  |  | I |  | I |  | I |  | I | R | R | R | R | Emre | I = INFORMATION
Key
R = RESPONSIBILITY
A = ACCOUNTABILITY
C = CONSULTATION
I = INFORMATION