## PID
Severity | [6 empty] | Risk | Implication | Severity | Likelihood | Risk Rating | Risk Mitigation Plan
Catastrophic | 5 | 5 | 10 | 15 | 20 | 25 | - | - | 5 | 5 | 25
Significant | 4 | 4 | 8 | 12 | 16 | 20 | - | - |  |  | 0
Moderate | 3 | 3 | 6 | 9 | 12 | 15 | Management Risks
Low | 2 | 2 | 4 | 6 | 8 | 10 | Lack of Validation and Verification | Product isn't acceptable to Investors | 5 | 2 | 10 | Develop a robust Verification and Validation Plan
Negligible | 1 | 1 | 2 | 3 | 4 | 5 | Delay in planning process | Delay in project end date | 3 | 3 | 9 | Allow upper and lower bounds in project time
|  | 1 | 2 | 3 | 4 | 5 | Technical risks
Likelihood |  | Improbable | Remote | Occasional | Probable | Frequent | Design error | End product does not meet requirements | 5 | 1 | 5 | Verification plan
[7 empty] | Arm doesnt meet minimum Specification | Not what the customer requires | 4 | 1 | 4 | Create a clear Stakeholder requiremenmts diagram and use the verification plan
Key | [6 empty] | Software malfunction | Arm doesnt complete the required task | 4 | 1 | 4 | Extensive testing of software and hardware, verification plan
Green | Minor Risk Mitigation Plan needed | [5 empty] | Legal and Contractual
Yellow | Modirate Risk Mitigation Plan needed | [5 empty] | Patent Infringement | Liable to legal action | 4 | 1 | 4 | Follow legal requirements and keep all documentation, part of the Validation plan
Orange | Significant risk mitigation plan needed | [5 empty] | Corporate espionage | Loss of money, lower profits | 4 | 1 | 4 | NDA contracts, dispose correctly of legal documents
Red | Have a Comprehensive Risk mitigation plan | [5 empty] | Economic
[7 empty] | Increase in mirco-chip cost | Increase in parts cost, lowering proffits | 3 | 1 | 3 | Use off the shelf components, run the arm on as little compute as possible so what chip is used is of limmited significance
[7 empty] | Unproportional increase in interest rates | Lower budget, liquidation | 3 | 1 | 3 | Insure loans against the market, assuming borrowing to start up the company
[7 empty] | Insufficient lifetime funding | delay in project end date, termination | 4 | 1 | 4 | Have multiply revenue streams
Market
[7 empty] | No longer a desired product | Lower sales than necessary, start up colapses | 5 | 1 | 5 | Keep in constant contact with stakeholders to insure the product is desirable to them
[7 empty] | Strong competition | Lack of sales, leading to lower profit | 3 | 4 | 12 | Have a superior product
Health and Safety
[7 empty] | Global Pandemic | Inability to meet in person | 5 | 2 | 10 | Verification and Verification plan that works online, have online meetings, use Github so all files are readily accessable by everone
[7 empty] | Mechanical injury/Arm colliding with a person | Legal action, loss of profits, delay in project | 4 | 3 | 12 | Outline necessary health and saftely plan fopr customers, limmit the potential speed nad torque of the arm
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 6
[9 empty] | 0 | 0 | 4