## Verification and Validation Mat
For requirements and notes see Requirements List document
Requirement ID | Description | Lead team member's | Initial Verification |  |  | Additional Verification |  |  | Stakeholder it links to | Stakeholder sign off | Notes | Key
|  |  | ID | Type of Verification | Coverage | ID | Type of Verification | Coverage |  |  |  |  | Full Coverage
1 | Minimum Working Envolope | AML & 3DD | 1.1 | Physical | Full | 2.1 | Analytical | Partial | All | UWE fet team |  |  | Partial Coverage
2 | Design a Gripper | PM & 3DD | 4.1 | Review | Full | 1.2 | Physical | Full | University | University |  |  | Inadequate Coverage
3 | Robot Cost XX | EPL & TA | 4.2 | Review | Full |  |  |  | Hobbyist's | Hobbyist's
4 | Measures and moves resistor within 10 seconds | EPL & AML | 3.1 | Code | Partial | 1.3 | Physical | Partial | All | UWE fet team | The two partials overlap to create a full in this case
5 | Be able to sort 12 resitors, and collect all unknow resistors in one location | EPL | 3.2 | Code | Partial | 1.1 | Physical | Partial | All | UWE fet team | The two partials overlap to create a full in this case
6 | 5 Year life span | All | 4.3 | Review | Full |  |  |  | All | UWE fet team
7 | Factor of saftey: 1 | TA & PM | 4.4 | Review | Partial | 1.4 | Physical | Full | University & Labs | UWE fet team
8 | Be ablt to lift 267mg | PM & EPL | 1.5 | Physical | Full |  |  |  | All | University
9 | Sort resistors into the correct box 99% of the time | EPL & AML | 3.3 | Code | Partial | 2.2 | Analytical | Full | All - Uni and labs most | University
10 | Health and saftey documentation | TA | 4.5 | Review | Full |  |  |  | All | UWE fet team
11 | Affordable | All | 4.2 | Review | Full |  |  |  | All | Hobbyist's
12 | Bluetooth | EPL & TA | 2.3 | Analytical | Partial | 3.4 | Code | Partial | All | UWE fet team | The two partials overlap to create a full in this case
13 | App controlled | EPL & PM | 3.5 | Code | Full |  |  |  | Hobbyist's | Hobbyist's
14 | Robot price competative | All | 4.6 | Analytical | Full
|  |  |  | Project Manager | PM |  |  |  | Document sign off
|  |  |  | Electronics and Programming lead | EPL |  |  |  | Dominic | James |  | John | Saad | Emre
|  |  |  | Algorithmic and Mathematical Lead | AML |  |  |  | Yes | Yes |  | Yes | Yes | Yes
|  |  |  | 3D Design Manager | 3DD
|  |  |  | Technical Administrator | TA |  |  |  | Stakeholder sign off | Which Stakeholder
[9 empty] | Yes | UWE Fet Team

## Verification ID
Verification ID | Type | Explanation | ID Key
1.1 | Physical | Pulling Arm out to 50cm | 1.x | Physical | Analysis
1.2 | Physical | 3D printing redesigned parts | 2.x | Analysis | Code
1.3 | Physical | Arm can move anywhere in its workling envelope in 5 seconds | 3.x | Code | Review
1.4 | Physical | Arm hold its self together while in use | 4.x | Review from team members
1.5 | Physical | Electromagnet can hold more than one resistor at a time to well over the 267mg required
2.1 | Analysis | Calculating how much arm extension was needed to reach the working envelope
2.2 | Analysis | Code gets the measured resistance correct
2.3 | Analysis | Bluetooth module on the PCB/Arduino
3.1 | Code | Code can measure resistance and decide where the resistor needs to go in 5 seconds | Document sign off
3.2 | Code | Test code can define resistance and tell the arm to move to the correct place | Dominic | James |  | John | Saad | Emre
3.3 | Code | Code gets measured resistance and moves to what it thinks is the correct box | Yes | Yes |  | Yes | Yes | Yes
3.4 | Code | Code can run and be sent using bluetooth
3.5 | Code | Possibility to run code in app | [6 empty] | Stakeholder sign off | Which Stakeholder
4.1 | Review from team members | Everyone collaborated on the new gripper design | [6 empty] | Yes | UWE Fet Team
4.2 | Review from team members | Everyone agreed and signed off on all orders, documentation was kept
4.3 | Review from team members | All committed to parts which individually are rated over 5 years of use
4.4 | Review from team members | No parts broke due to stress or use
4.5 | Review from team members | Document reviewed by all and meets standards
4.6 | Review from team members | A financial plan is produced